## User Story Breakdown
Story Id | User Story | Tasks | Estimated Hours | Actual Hours
1 | As user I should be able to register and securly login to Savr app so I can keep my personal data safe and secure | Register page UI | 2
|  | Register page backend | 2
|  | Login page UI | 1
|  | Login page backend | 2
|  | Write online help - User register and login | 1
|  | Write unit tests | 1
|  | Run unit tests | 1
|  | Write acceptance tests and review | 1
|  | Run acceptance tests | 1
|  | Fix bugs | 1
2 | As user I should be able to add, edit, and delete income entries so I can manage my income | Add income entry UI | 1
|  | Edit income entry UI | 1
|  | Delete income entry UI | 1
|  | Add, edit, delete income - backend API endpoints | 4
|  | Write online help - Add, edit, delete entries | 1
|  | Write unit tests | 1
|  | Run unit tests | 1
Write acceptance tests and review
Run acceptance tests
|  | Fix bugs | 1
3 | As user I should be able to view a summary dashboard showing total income, expenses and savings so I cam manage my financial activities accordingly | Create Dashboard UI | 2
|  | Create income view | 1
|  | Create expenses view | 1
|  | Create savings view | 1
|  | Dashboard income, expenses and savings - backend API endpoints | 4
|  | Write online help - Dashboard features | 1
|  | Write unit tests | 1
|  | Run unit tests | 1
Write acceptance tests and review
Run acceptance tests
|  | Fix bugs | 1
|  | Total Estimated Hours | 37
|  | Total Actual Hours | 0